***Project Proposal Name Domestic Violence Advocate Name of Agency or Individual Crisis Center and Women’s Shelter***

***County Marion Amount Requested $10,000***

# Indianola DCAT Mini Grant Projects

# RESULTS MATRIX FY16

|  |  |  |  |
| --- | --- | --- | --- |
| **Goals**  **&**  **Objectives** | Program/ServiceComponents | Action StepsandTime Frames | Program/Service Outcome & Performance Measures *(What is the expected measurable result? How will it be measured throughout the project period?)* |
| \*To increase the availability of a Domestic Violence Advocate by 50% in Marion County. **Accomplished by advocated going from 20 hours per week to 40 hours with DCAT Grant.**  Increase the number of community volunteers by 200% **Not Accomplished see Program Services Outcomes and Performance Measures** | Replace a half-time Domestic Violence Advocate with a full-time Advocate to have a greater presence in Marion County to better serve victims and the community.    Advocate will participate in community meetings and events.  Recruit and train 4 volunteers to assist with direct services and fundraising. | \*Advertise position mid-June  Hire late-June  Train and orient during July  Provide Advocacy services July-June 2016 – **Accomplished 1st qtr**    \*Advocate will identify community meetings in July and August.  Advocate will attend and participate in community meetings intended to address issues related to human services.  Advocate will identify service and religious organizations in July and August.  Advocate will present DV issues to these organizations throughout the year.  **Accomplished for FY 16**  \*Run ads for volunteers in August, provide training in September.  **Accomplished 1st qtr.** | \*We expect to serve 50 more victims of Domestic Violence in FY2016 with the presence of a full-time advocate.  **Clients served: 86 unduplicated within fiscal year.**  \*We expect the number of professional contacts to increase by 100%.  We will count the number of community meetings and speaking engagements the advocate has participated in.  Professional contacts: 283  Professional meetings/speaking engagements: 12  **Professional Contacts Increased 127%**  Four trained volunteers will assist with advocacy, and outreach in FY16. **Two volunteers hired**  We continue working toward building our volunteer pool in Marion County. A new tool for online training is been prepare by ICADV to assist individuals access required trainings online. |

Success Story

Our county advocate has been assisting a domestic violence survivor for about 2 years. The client received advocacy services and was assisted to build a safety plan. The client was able to leave the abusive relationship. The client continues receiving advocacy services and has expressed that our support, counseling and services were imperative in the decision process of whether or not leaving the abusive relationship. The client has expressed a desire to be independent and move forward in life.