***Attachment C***

***Project Proposal Name:* Wee Care Respite Program *Name of Agency or Individual:* Child Abuse Prevention Council**

***County:* Warren**

# Indianola DCAT Cluster Spring Projects

# RESULTS MATRIX FY16 - 2nd Quarter Report

|  |  |  |  |
| --- | --- | --- | --- |
| **Goals**  **&**  **Objectives** | Program/ServiceComponents | Action StepsandTime Frames | Program/Service Outcome & Performance Measures *(What is the expected measurable result? How will it be measured throughout the project period?)* |
| Children will thrive in safe and stable homes and parents will have support in their role as primary caregiver. | **Wee Care**:  -maintains full state childcare licensure  - adheres to the PCA Iowa Monograph on Documented Best Practice for Respite Services  -provides free services for any Warren County family with a child 6 wks. thru Kindergarten  -Uses research based curriculum:: *Al’s Pals: Kids Making Healthy Choices* (SAMSHA) and the well-researched *Care for Kids* sexual abuse prevention curriculum*.*  -Six ,2-hr sessions available per week (Sept-May) & four, 2-hr sessions /wk available June-Aug)  -provides parent education and one-on-one support at every session  -referrals to Early Access/AEA and other community services | Minimum of 140 families and 225 children served per year. **Update: 102 families & 175 children served in 1st six months**  **Update: 4,416 hours of respite care provided year to date**  **Update: State childcare licensing inspection conducted and full state childcare licensure renewed effective 10/1/15**  Referral to appropriate agencies for evaluation and services as needed. **Update: 20 "new" referrals to AEA/Early Access and 32 children previously referred still being served in the program**  Utilize *Al’s Pal’s* and *Care for Kids* curriculum weekly with children in the classroom. **(Ongoing)**  Provide information on parenting classes, offer classes onsite, parenting handouts, access to parent resource library, one-on-one -support. for parents **Update: 107** **referrals to community resources in 1st six months and 33 items checked out of lending library**  Actively promote program availability, recruit families, solicit referrals and offer programming. **(Ongoing)** | **30% of children served year-to- date have been referred to AEA/ Early Access**  **All children have up-to-date immunizations and physicals on file**  **\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\***  \*Parents will know how to get help for their family. **\***  \*Parents will report their family stress level had decreased**\***  \*Parents will increase knowledge about parenting and child development.**\***  \*Parents will report improved parent-child nurturing and attachment**\***  \*Parents will report improved family functioning **\***  *\*Data related to these outcomes will be reported after parents complete the written program evaluation in 4th qtr* |